Project Planning Phase
Team ID
PNT2022TMID21611
Project Name
Industry Specific Intelligent Fire Management System
Product Backlog, Sprint Schedule, and Estimation (4 Marks)
Functional
User
User Type
User Story / Task
Acceptance
Priority
Requirement
Story
criteria
(Epic)
Number
Assembling
Sprint-1
USN-1
As a user, I must position
I have access to
High
the sensors in the
my sensor
appropriate location.
triggers
USN-2
As a user, I must test my
I can use the serial
High
hardware to ensure that it
monitor to keep track of
is operational.
all sensor values.
Sprint-2
User
USN-3
As a user, I can create
I can sign up and utilize
Medium
Registration
user accounts for the
user Login to access the
model's essential
dashboard.
software.
USN-4
As a user, I can verify that
High
I can verify the
notifications and SMS are
alerts via Fast2SMS
delivered properly
Cloud
USN-5
As a user, I can keep
I can constantly monitor
High
Monitoring
track on how long data is
and obtain sensor data.
kept in IBM Cloudant

---
Total Story
Sprint End Date
Sprint Release Date
Sprint
Duration
Sprint Start Date
Story Points
Points
(Planned)
(Actual)
Completed (as on
Planned End Date)
20
6 Days
24 Oct 2022
29 Oct 2022
20
28 Oct 2022
20
6 Days
31 Oct 2022
05 Nov 2022
20
03 Nov 2022
Sprint-3
20
6 Days
07 Nov 2022
12 Nov 2022
20
12 Nov 2022
Sprint-4
20
6 Days
14 Nov 2022
19 Nov 2022
20
19 Nov 2022
Velocity:
Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration
unit (story points per day)
𝑽𝒆𝒍𝒐𝒄𝒊𝒕𝒚
𝟐𝟎
AV =
=
= 3.33
𝑺𝒑𝒓𝒊𝒏𝒕 𝑫𝒖𝒓𝒂𝒕𝒊𝒐𝒏
𝟔

---
Burndown Chart:
A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum.
However, burn down charts can be applied to any project containing measurable progress over time.